# Campaign Content Brief: Field Notes

A channel-ready brief connecting one campaign objective to audience insight, messages, assets, and approvals.

| Campaign | Field Notes - autumn collection |
| --- | --- |
| Client | Atlas & Finch Homeware |
| Campaign owner | Morgan Lee |
| Creative lead | Avery Chen |
| Flight | 2026-10-05 to 2026-11-01 |
| Budget | USD 42,000 paid media; production approved separately |

# Objective and success measures

Introduce the autumn modular-storage collection and convert high-intent visitors into collection-page sessions and email subscribers.

12,000 qualified collection-page sessions

1,200 new email subscribers at or below USD 3.50 each

Paid-social click-through rate of at least 1.4%

At least 80% of delivered assets accepted on first review

# Audience insight

Audience: Design-aware renters and first-time homeowners furnishing compact spaces.

Tension: They want calm, durable rooms but expect storage products to look bulky or temporary.

Desired response: This collection was designed around the space I actually have.

# Message hierarchy

Lead: Make more room without making the room about storage.

Support: Modular widths combine cleanly across awkward walls and changing homes.

Proof: Solid ash fronts, replaceable fittings, measured diagrams, and a five-year repair programme.

CTA: Plan your wall.

# Deliverables

| Channel | Asset | Variants | Owner | Due |
| --- | --- | --- | --- | --- |
| Landing page | Hero, comparison module, FAQ copy | Desktop + mobile | Avery | 2026-09-18 |
| Paid social | Static concept set | 6 concepts x 2 ratios | Imani | 2026-09-21 |
| Paid social | 15-second motion cut | 3 hooks x 2 ratios | Leo | 2026-09-24 |
| Email | Launch sequence | 3 sends x 2 subjects | Nora | 2026-09-25 |
| Organic | Product education carousel | 4 carousels | Imani | 2026-09-28 |

# Creative guardrails

Show real scale with dimensions or familiar objects in frame.

Use warm daylight, quiet backgrounds, and occupied rooms rather than empty sets.

Never imply that every configuration fits every wall; link to measured diagrams.

Provide descriptive alternative text and caption all motion assets.

Avoid unsupported environmental superlatives and countdown-style pressure.

# Workflow and approvals

Review rounds: Two consolidated rounds in the project board.

Final approval: Morgan Lee for commercial claims; Priya Shah for legal and sustainability copy.

Measurement: UTM naming follows field-notes / channel / creative-id; dashboard owner is Sam Ortiz.

Fictional campaign sample. Confirm claims, rights, accessibility, and channel specifications before publishing.