## Risk register
Project Risk Register
A scored delivery-risk register with owners, mitigations, triggers, and review dates.
Project | Aurora 4.2 release
Owner | Priya Nair
Review cadence | Every Tuesday
Scoring | Probability x impact; 15-25 high, 8-14 medium, 1-7 low
ID | Risk | Category | Owner | Probability | Impact | Score | Response | Trigger | Next review
R-01 | Migration exceeds the approved maintenance window. | Schedule | D. Okafor | 3 | 5 |  | Rehearse rollback and split the largest tenant batch. | Dry run exceeds 70 minutes | 2026-08-04
R-02 | Accessibility defects block public release. | Quality | A. Bello | 2 | 5 |  | Run keyboard and screen-reader checks on each release candidate. | Any critical WCAG issue | 2026-08-04
R-03 | Support coverage is insufficient during cutover. | People | N. Brooks | 3 | 3 |  | Publish rota and escalation matrix two weeks before launch. | One uncovered four-hour block | 2026-08-11
R-04 | Third-party search index lags after catalogue import. | Dependency | S. Rossi | 4 | 3 |  | Pre-warm index and retain legacy search read path for 24 hours. | Index lag exceeds 10 minutes | 2026-08-04
R-05 | Analytics event names drift between web and mobile. | Data | T. Baxter | 2 | 4 |  | Validate both clients against the signed event dictionary in CI. | Schema diff in release build | 2026-08-06
R-06 | Translation arrives after the final content freeze. | Schedule | M. Laurent | 2 | 3 |  | Book linguistic review early and define an English fallback window. | Two locales miss beta cutoff | 2026-08-11
R-07 | Peak checkout load exceeds the revised capacity model. | Performance | D. Okafor | 2 | 5 |  | Load-test at 1.5x forecast and pre-approve temporary capacity. | P95 exceeds 900 ms | 2026-08-06
R-08 | Launch copy includes an unapproved performance claim. | Compliance | P. Shah | 2 | 4 |  | Require claim source and legal owner in the content checklist. | Claim lacks evidence link | 2026-08-08
Fictional project sample. Scores prioritise discussion; they do not replace professional risk judgement.