## Budget
Event Plan — Customer Appreciation Evening
Date: 2026-03-14 · Venue: Harbor Hall · Guests: 80
Item | Estimated | Actual | Difference
Venue hire | 1200 | 1200
Catering | 2400 | 2510
Drinks | 900 | 860
Decor | 350 | 300
Printing | 180 | 165
Total

## Tasks
Task | Owner | Due | Status
Book venue | Priya | 2026-02-01 | Done
Confirm catering | Sam | 2026-02-15 | In progress
Send invitations | Maya | 2026-02-20 | To do
Order decor | Priya | 2026-03-01 | To do